## Bug Report
Automation Exercise Defect Reports
Project: Automation Exercise Ecommerce Website QA Testing ¦ Record one independently reproducible defect per row
Total Defects |  |  | Open |  |  | High/Critical |  |  | Ready for Retest |  |  | Notes:
2 |  |  | 2 |  |  | 1 |  |  | 0
Defect IDA7:J17A1A7:A7:P17 | Related Test Case | Module | Defect Type | Summary / Title | Severity | Priority | Environment | Preconditions | Steps to Reproduce | Expected Result | Actual Result | Status | Reported By | Date Reported | Evidence / Screenshot | Assigned To | Resolution / Developer Notes | Retest Status | Retest Date | QA Notes
AE-BUG-001 | AE-LOGOUT-001 | Logout | Session / Navigation | Authenticated user information remains visible after logout when navigating back | Medium | High | Web application Browser/OS: Record during execution URL: https://automationexercise.com | 1. Active registered test account exists. 2. User begins logged out. | 1. Open Automation Exercise. 2. Click Signup / Login. 3. Enter valid registered credentials. 4. Click Login. 5. Confirm “Logged in as [username]” is displayed. 6. Click Logout. 7. Click the browser Back button. 8. Observe the page. 9. Refresh the page and attempt to open an authenticated feature to verify whether access persists. | After logout, browser navigation should not display authenticated user information or provide access to authenticated functionality. | After logout, clicking the browser Back button displayed the previous page with “Logged in as Kevin Tester” and the Logout option. Further verification is required to determine whether the page was cached or the authenticated session remained active. | Open | KM | 2026-07-29 | Add a redacted screenshot showing the stale authenticated interface. |  |  | Not Retested |  | Potential cached page behavior. Confirm session state by refreshing and accessing a protected feature before final severity assessment.
AE-BUG-002 | AE-LOGOUT-001 | Logout | Error Handling / Information Disclosure | Repeated logout request causes an unhandled KeyError and exposes internal debugging information | High | High | Web application Django 3.2.8 shown in response Python 3.7.17 shown in response URL: https://automationexercise.com/logout | 1. Active registered test account exists. 2. User begins logged out. | 1. Open Automation Exercise. 2. Click Signup / Login. 3. Enter valid registered credentials. 4. Click Login. 5. Click Logout. 6. Click the browser Back button. 7. Click Logout again. | The application should safely handle the repeated logout request and redirect the unauthenticated user to Signup / Login without displaying an error or internal information. | The application displayed “KeyError at /logout” because the user_id session key was missing. A Django debug page exposed framework and Python versions, server paths, traceback details, cookies, and session-related information. | Open | KM | 2026-07-29 | Add only a sanitized screenshot. Redact all cookie, session, username, token, and path values. |  |  | Not Retested |  | Security-relevant information disclosure. The original screenshot must not be published without extensive redaction.